## Coherence review
Pier cap coherence review
D2 I-95 Pedestrian Bridge • October 9, 2026 • BPAD: geometry and source references only. Steel stays in this review and the report.
Fill yellow columns E–G. Include units and identify model/detail files. Save and return this workbook when ready.
Sources: Pier Cap Design 10-9.html, matching Pier_MinTip.XML, and current BPAD. Source fingerprints and reconciled values are below.
Item | Review topic | Finding and current treatment | Decision or information needed | Your decision | Your instructions | New values / supporting files
01 | C005 / separate steel | C005 is completely unchanged by your direction, retaining earlier steel, forces and a 3.44-in end-detail allowance. BPAD receives geometry and source references only (3-in current end-detail allowance). Current steel is kept in the separate report and this Excel review. | No decision needed: your instructions are recorded at right. Differences remain explicit; no claim is made that C005 checks the current report cage. | Keep as noted | Do not update calc C005. Geometry and source references only in BPAD; keep reinforcement details in the separate pier report and Excel review. User direction, October 9, 2026.
02 | Right bearing-row offset | Exact source XML: left row Y = −10.50 in, right row Y = +10.14 in. The journal uses ±10.50 in. Right-row difference = 0.36 in. Bearing labels 1L/2L/1R/2R are correct; cap connections are 16/33 and bearing nodes are 181–184. | Specify the intended right-row offset. Direct whether the journal or model should change and whether to rerun affected load-transfer/design results. | Discuss | I need to correct the FBMP model I think there is a typo in it. I'll update the model and reupload the report.
03 | Pier U-bar conflicts | Source R2/R4/R6/R8 #6 U-bars clash with pile/clearance envelopes. Ends: 90° bends, 9-in straight tails, 4.5-in inside bend diameter. The prior end-bent field-hook direction has not been assumed to resolve the pier detail. | Specify how to handle the pier hooks, identify a revised detail, or request alternatives. Revised geometry and development/anchorage checks remain necessary to close the conflict. | Keep as noted | U bars tails can be field bent to accommodate a potential clash
04 | Longitudinal tension reference | The report’s N uniform-reference check requires 4.287 in² versus 3.080 in² credited (1.760 main + 1.320 side): 1.207 in² shortfall. It is labeled REFERENCE, not an actual-cage failure. Passing flexure and “0 failed checks” do not resolve it. | Direct an actual-cage longitudinal force/load-path evaluation, a reinforcement revision, or a documented disposition of this reference shortfall. | Discuss | Explain to me in chat what the N uniform check is all about
05 | Model and journal load inputs | The exact local XML matches the report. Geometry, bearing spacing, effective pipe properties and superstructure DC reconcile to printed precision. Full wind inputs, local below-pad weights, transfer moments, combinations and convergence have not been certified against the current journal. | Confirm this is the controlling pier model. Choose a full load-input comparison/update, a rerun after corrections, or retention as an explicitly identified source snapshot. | Discuss | Will need to provide an update cap design report as the latest.
06 | Wind, walls and old sketches | Cap length is 230 in; the journal wind face is 231 in. The quantity sheet also retains earlier three-beam / 19-ft-3-in sketches. Wall/fin, crash-wall and cheek-wall quantities are separate from the cap report. Cap volume remains 230 ft³; pier pedestals remain 48 in. | Confirm the intended wall/wind envelope and provide wall dimensions. Direct which wind loads, quantities and historical sketches to update, label or defer. | Update | Use the cap length from the report
07 | Remaining engineering checks | Original source count: 48 pending/conditional. Service III is already N/A by your prior direction. Fatigue, development, anchorage, hoop closure, force zones, D-regions/pile-head load transfer, code/exposure basis and omitted axial/weak-axis/lateral actions remain separate. | Specify checks to complete, defer or exclude and the criteria/details/actions to use. Do not treat independent maximum actions as a concurrent force vector. | Defer | Leave as is
08 | Construction spacing and takeoff | Adjacent-run transverse bars have 2.00 in clear, exactly the source minimum (D/C 1.000). Pile-to-bar clearance is a separate 1-in input. Gross steel is 1171.89 lb and excludes laps, closure extensions, undrawn end anchorage and waste. | Confirm the clearance/tolerance basis and whether the actual cage needs added spacing margin. State whether to develop a fabrication-level steel takeoff with the missing allowances. | Defer | Leave as is we can deal with this issue in shops later
09 | Inherited reference links | The current journal has zero stored errors. Three preexisting LoadCombinations links are unresolved: two references to CodePage42 and one to CodePage14. They remain outside the pier source update. | Choose repair now, defer, or address separately. Provide the intended references if known. | Update | repair now
Recorded design basis and reconciled data
Reference values below describe the supplied design. Responses belong in the yellow cells above. Source screening is not final design approval.
| Recorded item | Current value / basis | Units / qualification
| Cap width | 48 | in; report and live project geometry agree
| Cap depth | 36 | in; report and live project geometry agree
| Cap length | 230 | in = 19 ft 2 in; separate from 231-in wind face
| Pile arrangement | Four 20-in pipe piles at 60-in centers | Cap-end center stations: 25, 85, 145, 205 in
| End face allowance | 15 | in = 9-in edge + 3-in tolerance + 3-in detail allowance
| Pile embedment / covers | 12-in embedment; 3-in covers | Physical embedment and top/bottom/side clear covers
| Top main steel | 4 #6 continuous | One row; 1.76 in²
| At-pile bottom steel | 4 #9 continuous | Two bars each side of pile envelope; 4.00 in²
| Between-pile bottom | 4 #9 + 4 ADDITIONAL #6 hooked bars | Combined main area 5.76 in²; added bars at 6-in pitch
| Skin per side | 3 #6 continuous | 1.32 in² per side; distinct from main flexural areas
| Transverse schedule | 19 closed #6 hoops + 16 #6 pile U-bars | Nine runs; nominal 9-in pitch with fitted end bars; total 35
| Concrete gross volume | 230 | ft³; unchanged; excludes walls/pedestals and pile deductions
| Steel gross estimate | 1171.89 | lb; source quantity excludes laps/closures/undrawn anchorage/waste
| Strength M− / M+ pile / M+ span | 33.65 / 163.18 / 369.38 kip-ft | Independent factored maxima; not one concurrent vector
| Strength shear / torsion | 218.27 kip / 24.97 kip-ft | Both shear zones use 218.27 kip
| Service I N / P / B | 20.83 / 125.69 / 315.31 kip-ft | Service III N/A by prior user direction; fatigue separate
| Bearing stations | 63.50 / 166.49 in from cap end | XML stations 38.50 / 141.49 in + 25-in datum shift
| Effective pipe wall | 0.475 | in = 0.625 − 0.150; XML prints 0.48 in
| Pipe area / inertia | 29.14 in² / 1389.26 in⁴ | XML agrees with 0.475-in effective section to displayed precision
| Superstructure DC | 92.07 kip each left; 89.97 kip each right | Journal agrees to 0.01 kip; full load audit remains Item 05
| Source check summary | 0 failed; 48 pending/conditional; max D/C 1.000 | Historical report summary, not rerun after Service III disposition
| Report SHA-256 | 806a47bb50962827f5fd3e6fdd4c42c8b41851bddd23ff3948f377fe6a48b7b2 | Pier Cap Design 10-9.html; original in Downloads
| Matching XML SHA-256 | cb094424ed16e60b16957ed84a62aea21533fb61671c58a27ca73a997eaf70e4 | Pier_MinTip.XML; exact local file matches report
| Journal base SHA-256 | 4cdc73c485443fd22aaa77eff17ea1faeec30f9ba143be881b5d6c9676189625 | Actual journal at start; preserved intervening user changes
| Journal task | T005 — geometry and source references only | C:/github/D2MPDB/journal/D2_I95_Project_Journal.bpad
| Preservation | Six bounded components; C005 entirely unchanged | Existing material interfaces, end-bent record, resources and 31 relative PDF references retained
| Acceptance scope | Geometry / source references; steel separate | C005 unchanged. Final structural adequacy, corrected U geometry and full project coherence remain open